## Sheet1
FIIT STU
Displaying 5 issues at 09/May/14 4:40 PM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Created | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | DueTime | PercentDone | Units | Sprint | Epic/Theme | Story Points | Business Value | Rank | Epic Link | Flagged
Robocup_tp09 | ROBOCUPTP-230 | Priprava agenta na robocup turnaj | Story | Open | Major | Unresolved | Unassigned | Roman Moravcik | 09/May/14 4:37 PM | 09/May/14 4:37 PM |  |  |  | AllTeam_04_09, Team_09 |  | 0 | 1 |  | 28800 | 28800 |  | 0% |  |  |  | V ramci tejto ulohy je nutne otestovat jednotlive highskilly a doplnit fre run mod. |  | 0% | 0% |  | 28800 | 28800 |  |  |  | 3 | Sprint 11 |  |  |  | 5
Dalej je potrebne skontrolvoat ant proces na deploy agenta so vsetkymi potrebnymi kniznicami.
Robocup_tp09 | ROBOCUPTP-226 | Doplnenie a dokoncenie dokumentacia | Story | Open | Major | Unresolved | Michal Blanarik | Tomas Nemecek | 25/Apr/14 11:43 PM | 09/May/14 4:35 PM |  |  |  | Team_09 |  | 0 | 1 |  | 144000 | 136800 | 7200 | 5% |  |  |  | Cielom je dokoncit a sfinalizovat celu dokumentaciu timoveho projektu |  | 5% | 5% | 7200 | 136800 | 144000 |  |  |  | 14 | Sprint 10, Sprint 11 |  |  |  | 4
Robocup_tp09 | ROBOCUPTP-224 | Testovanie projektu | Story | Open | Major | Unresolved | Martin Markech | Tomas Nemecek | 25/Apr/14 11:30 PM | 09/May/14 4:35 PM |  |  |  | Team_09 |  | 0 | 1 | [8 empty] | Testovanie funkcnosti projektu odovzdaneho druhym timom. Testovanie bude spocivat v otestovani striedania strategii a taktik podla dopredu stanoveneho planu. Dalej sa budu kontrolvoat ci su vybrane spravne situacie podla stavu hry. | [9 empty] | 6 | Sprint 10, Sprint 11 |  |  |  | 1
Spisat protokol
- ako vybera taktiky
- ako vybera strategie
5 use case - rozlozeni na ihrisku. Popisat i kod/kvalitu?
Robocup_tp09 | ROBOCUPTP-196 | Optimalizácia highskill-u Kick | Improvement | Reopened | Major | Unresolved | Roman Moravcik | Roman Moravcik | 20/Mar/14 11:47 PM | 09/May/14 4:35 PM |  |  |  | Team_09 |  | 0 | 1 |  | 14400 | 0 | 39000 | 270% |  |  |  | Kick aktuálne nepočíta s natočením sa k lopte. Architektúra je postavená podľa zlej implementácie Walk takže je potrebné Kick upraviť aby používal dohodnutú architektúru pre highskill. |  | 100% | 100% | 39000 | 0 | 14400 |  |  |  | 2 | Sprint 8, Sprint 9, Sprint 9.1, Sprint 10, Sprint 11 |  |  |  | 3
Robocup_tp09 | ROBOCUPTP-146 | Vytvorenie defaultneho lowskillu a highskillu | Task | Open | Minor | Unresolved | Stefan Horvath | Martin Markech | 05/Mar/14 9:21 PM | 09/May/14 4:38 PM |  |  |  | Team_09 |  | 0 | 1 |  | 5400 | 5400 |  | 0% |  |  |  | Vytvorenie default low a high skillu, ktory by sa vykonaval ak ziaden low/highskill nevyhovuje - hrac by stal na mieste a otacal by hlavou za ucelom ziskavania informacii o stave ihriska |  | 0% | 0% |  | 5400 | 5400 |  |  |  | 2 | Sprint 10, Sprint 11 |  |  |  | 2
Generated at Fri May 09 16:40:01 CEST 2014 by Tomas Nemecek using JIRA 5.1.6#785-sha1:8d9ee55efd0253d225a09d2c55f2f71a303affe4.