## Sheet1
FIIT STU
Displaying 9 issues at 16/Nov/14 10:24 PM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Sprint | Flagged | Epic/Theme | Units | Epic Link | PercentDone | Story Points | DueTime | Rank | Rank (Obsolete)
BigData | BIGDATA-24 | Cookie problem | Improvement | Resolved | Critical | Fixed | Vladimir Demcak | Vladimir Demcak | Vladimir Demcak | 20/Oct/14 7:41 PM | 16/Nov/14 10:24 PM | 29/Oct/14 6:08 PM | 29/Oct/14 6:07 PM |  |  |  |  | 0 | 2 |  | 10800 | 5400 | 5400 | 50% |  |  |  | Problem s cookie z WOS autentifikacie. |  | 50% | 50% | 5400 | 5400 | 10800 |  | 2. šprint | [7 empty] | 0¦i00i9f: | 9.2234e+18
problem je ze cookie si treba "zapamatat" a pouzivat dlhsi cas kym neexpiruje.
Momentalne to funguje tak ze pri kazdom request sa ziskava nove cookie. Pripadne treba zrusit session pre tento cookie.
Z pdf minuleho roka:
Citujem:
"Jeden session zvládne maximálne 2 dopyty za sekundu. Session sa
uzatvára poslaním požiadavky na adresu
http://search.webofknowledge.com/esti/wokmws/ws/WOKMWSAuthenticate. Platnosť sa
stratí aj uplynutím určitého času. Telo požiadavky je nasledovné:
<soapenv:Envelope xmlns:soapenv="http://schemas.xmlsoap.org/soap/envelope/"
xmlns:auth="http://auth.cxf.wokmws.thomsonreuters.com">
<soapenv:Header/>
<soapenv:Body>
<auth:closeSession/>
</soapenv:Body>
</soapenv:Envelope>"
BigData | BIGDATA-23 | Vytvorenie wiki | Task | Closed | Major | Fixed | Jan Krivy | Jan Krivy | Jan Krivy | 19/Oct/14 4:39 PM | 05/Nov/14 12:42 PM | 23/Oct/14 10:14 AM | 19/Oct/14 4:41 PM |  |  |  | 22/Oct/14 | 0 | 1 |  |  | 0 | 7500 |  |  |  |  | Vytvorenie wiki v bitbucket repozitari za ucelom vedenia dokumentacie a ostatnych dokuemntov |  | 100% | 100% | 7500 | 0 |  |  | 2. šprint | [7 empty] | 0¦i00ibr: | 9.2234e+18
BigData | BIGDATA-21 | BIGDATA-6 Vytvorit "metodu" na servlete pre ZISKANIE referencie pre clanok na SCOPUS /elsevier.com/ | Sub-task | Closed | Major | Fixed | Martin Cibula | Vladimir Demcak | Vladimir Demcak | 18/Oct/14 7:18 PM | 05/Nov/14 12:41 PM | 13/Nov/14 2:15 PM | 29/Oct/14 6:09 PM |  |  |  |  | 0 | 3 |  |  | 0 | 14100 | [6 empty] | 100% | 100% | 14100 | 0 |  |  | 2. šprint | [7 empty] | 0¦i00ibb: | 9.2234e+18
BigData | BIGDATA-20 | BIGDATA-6 Vyhladavat v scopuse diela cez meno autora a nazvu diela | Sub-task | Closed | Major | Done | Jozef Melko | Jan Krivy | Jan Krivy | 17/Oct/14 9:52 AM | 31/Oct/14 10:59 AM | 15/Nov/14 11:24 PM | 22/Oct/14 7:24 PM |  | 1.0.0 |  | 22/Oct/14 | 0 | 2 |  | 5400 | 0 | 22500 | 416% |  |  |  | Vlado vytvoril jednoduchy priklad, kde hladal autorov podla mena. |  | 100% | 100% | 22500 | 0 | 5400 |  | 2. šprint | [7 empty] | 0¦i00i9j: | 9.2234e+18
My potrebujeme spravit sluzby, kde budeme hladat dokument podla autora a nazvu dokumentu. Treba sa teda inspirovat jeho prikladom akurat staci spravit query na toto vyhladavanie.
Field codes pre query - http://help.elsevier.com/app/answers/detail/a_id/2347/p/8150
BigData | BIGDATA-19 | Vytvorenie tried entit + connection manager | Task | Closed | Major | Fixed | Marek Cernak | Marek Cernak | Marek Cernak | 16/Oct/14 7:37 PM | 25/Oct/14 11:37 PM | 29/Oct/14 5:57 PM | 29/Oct/14 5:57 PM | 1.0.0 |  |  | 22/Oct/14 | 0 | 2 |  | 5400 | 0 | 13200 | 244% |  |  |  | Vytvorenie databazovych entit v Jave a connection managera za pomoci nastroja Hibernate |  | 100% | 100% | 13200 | 0 | 5400 |  | 2. šprint | [7 empty] | 0¦i00i9b: | 9.2234e+18
BigData | BIGDATA-17 | BIGDATA-6 Ziskavat pomocou SCOPUSu cez servlet zakladne data | Sub-task | Closed | Major | Done | Vladimir Demcak | Vladimir Demcak | Vladimir Demcak | 16/Oct/14 6:41 PM | 31/Oct/14 10:59 AM | 31/Oct/14 10:59 AM | 29/Oct/14 6:10 PM |  |  |  | 19/Oct/14 | 0 | 2 |  |  | 0 | 18000 |  |  |  |  | - vyriesit autentifikaciu cez proxy server |  | 100% | 100% | 18000 | 0 |  |  | 2. šprint | [7 empty] | 0¦i00i97: | 9.2234e+18
BigData | BIGDATA-12 | Plány pre prvé 2 šprinty | Task | Resolved | Major | Fixed | Martin Sustek | Martin Sustek | Martin Sustek | 16/Oct/14 5:15 PM | 29/Oct/14 3:39 PM | 29/Oct/14 3:39 PM | 29/Oct/14 3:39 PM | 1.0.0 |  |  | 20/Oct/14 | 0 | 2 |  | 2700 | 0 | 3600 | 133% |  |  |  | 1. šprint spätne, 2. šprint aktuálne. Spísanie, zadokumentovanie, odoslanie vedúcej projektu |  | 100% | 100% | 3600 | 0 | 2700 |  | 2. šprint | [7 empty] | 0¦i00i7r: | 9.2234e+18
BigData | BIGDATA-6 | Vývoj základného servletu | Task | Resolved | Major | Fixed | Vladimir Demcak | Martin Sustek | Martin Sustek | 16/Oct/14 4:33 PM | 31/Oct/14 11:00 AM | 31/Oct/14 11:00 AM | 31/Oct/14 10:58 AM | 1.0.0 |  |  | 29/Oct/14 | 0 | 6 |  | 57600 | 0 | 162000 | 281% | BIGDATA-17, BIGDATA-18, BIGDATA-20, BIGDATA-21 |  |  | Úlohy identifikujú zainteresovaní (Vlado, Jožo, Marek, Martin). Na základe nich si potom vytvárajte subtasky v tejto issue. |  | 100% | 100% | 216600 | 0 | 63000 |  | 2. šprint | [7 empty] | 0¦i00i63: | 9.2234e+18
------------------------------------------
zdrojaky na git repository: https://bitbucket.org/BigDataFiit/bigdata v branch devel
import projektu
manual deploy projektu na server
1, arl6.library.sk:8080
2, manage app
3, login ako vsade
4, udeploy/deploy "/TP_team15"
5, export projektu ako war
6, "WAR file to deploy" Vybrat subor - DEPLOY
7, Done
BigData | BIGDATA-1 | Vytvorenie a setup bitbucket repozitara | Task | Closed | Major | Fixed | Martin Sustek | Martin Sustek | Martin Sustek | 16/Oct/14 11:48 AM | 29/Oct/14 3:40 PM | 29/Oct/14 1:23 PM | 25/Oct/14 11:38 PM |  | 1.0.0 |  | 18/Oct/14 | 0 | 2 |  | 1800 | 0 | 2460 | 136% |  |  |  | Na svojom konte spravit repozitar, prikazat vsetkym, nech si zalozia bitbucket ucet, pozvat vsetkych clenov, dat im write access |  | 100% | 100% | 2460 | 0 | 1800 |  | 2. šprint | [7 empty] | 0¦i00i5v: | 9.2234e+18
Generated at Sun Nov 16 22:24:42 CET 2014 by Martin Sustek using JIRA 6.3.8#6338-sha1:68f19fa1b0735858c317bd22f79afd47ceeab007.