## Sheet1
Story ID | Theme | Epic | Release name | Sprint name | Story status | Story type | Impediment | Ready indicator | Waiting flag | Story title | Description | Acceptance criteria | Moscow category | Business value | Risk | KANO | Effort | Story estimated time | Story remaining time | Story spent time | Story due date | Tags | Story color | Date of creation | Date of last completion
169184 |  | SEC |  |  | todo | user_story | false | false | false | Pridanie SEC pravidla | [6 empty] | 3.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-29 22:01:34 UTC
169220 |  | SEC |  |  | todo | user_story | false | false | false | Odstránenie SEC pravidla | [6 empty] | 2.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-29 22:30:03 UTC
169221 |  | SEC | Release 1 | Sprint 3 | todo | user_story | false | false | false | Zobrazenie SEC pravidiel | [6 empty] | 3.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-29 22:30:55 UTC
169223 |  | Logy |  |  | todo | user_story | false | false | false | Archivácia logov | [6 empty] | 5.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-29 22:38:07 UTC
169234 |  | Logy |  |  | todo | user_story | false | false | false | Nájednie logu k udalosti | [6 empty] | 8.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-30 08:53:53 UTC
169235 |  | Videnia |  |  | todo | user_story | false | false | false | Vytvorenie videnia | [6 empty] | 13.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-30 08:55:01 UTC
169236 |  | Filtre | Release 1 | Sprint 3 | in_progress | user_story | false | false | false | Vytvorenie filtra | [6 empty] | 5.0 | 360 | 360 | 0 |  |  | #FBFFA8 | 2016-10-30 08:57:54 UTC
169238 |  | Filtre |  |  | todo | user_story | false | false | false | Úprava filtra | [6 empty] | 2.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-30 09:57:16 UTC
169239 |  | Filtre |  |  | todo | user_story | false | false | false | Zobrazenie - tabuľka | [6 empty] | 2.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-30 09:58:56 UTC
169240 |  | Filtre |  |  | todo | user_story | false | false | false | Zobrazenie - čiarový graf | Neinteraktívny graf. | [5 empty] | 8.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-30 09:59:29 UTC
169241 |  | Filtre |  |  | todo | user_story | false | false | false | Odstránenie filtra | [6 empty] | 1.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-30 10:00:49 UTC
169242 |  | Videnia |  |  | todo | user_story | false | false | false | Otvorenie videnia v novom okne | [7 empty] | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-30 10:02:55 UTC
169243 |  | Videnia |  |  | todo | user_story | false | false | false | Manažment filtrov na videní | [6 empty] | 5.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-30 10:04:49 UTC
169245 |  | Filtre |  |  | todo | user_story | false | false | false | Export obsahu filtra | [7 empty] | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-10-30 10:06:38 UTC
173306 |  | Udalosti | Release 1 | Sprint 3 | todo | user_story | false | false | false | Formát udalosti | [6 empty] | 1.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-11-08 08:12:34 UTC
173343 |  | SEC | Release 1 | Sprint 3 | todo | user_story | false | false | false | Ukladanie logov do DB na pozadí | [6 empty] | 5.0 | 0 | 0 | 0 |  |  | #FBFFA8 | 2016-11-08 09:32:55 UTC
173346 |  | Používatelia | Release 1 | Sprint 3 | todo | user_story | false | false | false | Refaktorizácia používateľského rozhrania | [6 empty] | 13.0 | 600 | 600 | 0 |  |  | #FBFFA8 | 2016-11-08 09:35:50 UTC
173349 |  | Dokumentácia | Release 1 | Sprint 3 | todo | research | false | false | false | Dokumentácia k produktu | [6 empty] | 8.0 | 0 | 0 | 0 |  |  | #A8D2FF | 2016-11-08 09:44:58 UTC
173351 |  | Vývoj | Release 1 | Sprint 3 | todo | technical | false | false | false | Autodeploy | [6 empty] | 8.0 | 0 | 0 | 0 |  |  | #A8FFD4 | 2016-11-08 09:47:45 UTC